Service Excellence Pilot: Pilot Plan

Synthetic training data. Contains no patient data, no real customer data, and no confidential Topcon content.

Black Belt Consulting × AO Finland — Agentic Software Development Training, Day 1

Executive summary

The Service Excellence Pilot is a fictional internal initiative designed for Microsoft 365 Copilot and agent training. The pilot focuses on improving remote triage consistency and service-note quality for diagnostic equipment support.

It does not include patient data, clinical decision-making, warranty decisions, automated customer commitments, or live production system integration.

Objectives

Improve consistency of initial service notes.

Reduce ambiguity in handovers between service operations and product support.

Create a lightweight process guide that can be used as a knowledge source for a simple agent.

Teach verification habits: source checking, uncertainty handling, and safe refusal.

In scope

Remote triage categorization for synthetic service cases.

Required service-note fields and escalation criteria.

Internal training examples for Copilot and Copilot Studio.

Business-readable reporting for a fictional steering review.

Out of scope

Patient-identifying information or clinical interpretation.

Automated replies to customers.

Warranty decisions or contractual commitments.

Integration with production service management systems.

Replacing human review or quality approval.

Stakeholders

Mika Lehtonen — Pilot sponsor and steering summary owner.

Sofia Niemi — Service operations lead and required-fields approver.

Ravi Patel — Product support lead and synthetic case owner.

Laura Chen — Documentation owner and process-guide author.

Elena García — Quality and compliance reviewer.

Timeline

10 June 2026: Alignment meeting and scope decision.

13 June 2026: Required service-note fields confirmed.

17 June 2026: Draft process guide completed.

18 June 2026: Synthetic service cases completed.

20 June 2026: Guardrails and safety review completed.

24 June 2026: Steering summary packaged.

July 2026: Fictional steering review demo.

Success metrics

First-response completeness: percentage of synthetic cases with all required fields present.

Escalation accuracy: percentage of synthetic cases routed to the correct queue.

Ambiguity reduction: number of unclear ownership or missing-information flags identified before handover.

User confidence: qualitative feedback from business and technical learners.

Governance notes

All training content is synthetic and safe for demo use.

The agent should answer from the approved guide only.

If the answer is not in the guide, the agent should say so and redirect to the process owner.

In production, source documents require ownership, review date, approved storage, and lifecycle management.