Service Excellence Pilot: Risk and Dependency Notes

Synthetic training data. Contains no patient data, no real customer data, and no confidential Topcon content.

Black Belt Consulting × AO Finland — Agentic Software Development Training, Day 1

Risk register

| ID | Risk | Impact | Likelihood | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-01 | Overtrust in polished AI output | High | Medium | Require source-check prompt and visible verification in demos. | Elena García |
| R-02 | Regional terminology causes inconsistent categorization | Medium | High | Include synonym examples in process guide and synthetic cases. | Sofia Niemi |
| R-03 | Agent answers beyond approved guide | High | Medium | Add explicit instructions: answer only from source; refuse or redirect when unsupported. | Laura Chen |
| R-04 | Participants paste real sensitive data into demo | High | Low | Start demos and labs with clear synthetic-data-only instruction. | Mika Lehtonen |
| R-05 | Copilot Studio access unavailable for Track B | Medium | Medium | Prepare trainer-led fallback and screenshots. | Ravi Patel |

Dependencies

| ID | Dependency | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| D-01 | Required service-note fields confirmed | Sofia Niemi | 13 June 2026 | Open |
| D-02 | Process guide draft created | Laura Chen | 17 June 2026 | Open |
| D-03 | Synthetic cases prepared | Ravi Patel | 18 June 2026 | Open |
| D-04 | Guardrails reviewed | Elena García | 20 June 2026 | Open |
| D-05 | Copilot Studio access confirmed | Mika Lehtonen | Before training | At risk |

Trainer note

This document intentionally overlaps with the meeting transcript and pilot plan. Use it with the pilot plan and metrics workbook to ask Copilot for a one-page steering status report. Then ask Copilot to show gaps and source notes.